Grant Agreement N° IEE/08/495/SI2.528393

TABULA

Typology Approach 
for Building Stock Energy Assessment

Intelligent Energy – Europe (IEE)

SAVE / Altener

Progress Report

28-10-2011

Period covered: 				from 01-12-2010 to 31-08-2011				Due date: 	30-09-2011

Start date of the action: 	01-06-2009											Duration: 	36 months

End date of the action:		31-05-2012

Project co-ordinator:		Tobias Loga
	Institut Wohnen und Umwelt GmbH (IWU)
	(Institute for Housing and Environment)
	Annastraße 15
	D-64285 Darmstadt / GERMANY
e-mail: 	t.loga@iwu.de
phone: 	++49/6251/2904-53

Project website: 	www.building-typology.eu

Content

1	Progress Report Summary	3

1.1	Objectives of the period	3

1.2	Achieved results of the period	3

1.3	Identified problems and corrective actions taken in the period	3

1.4	Main activities until the end of the action	4

2	Consortium management in the period	4

3	Progress of work plan	6

3.1	Progress on work packages against initial objectives	6

3.2	Deviations from the project work plan	25

3.3	Interim review of deliverables	25

3.4	Interim review of performance indicators	26

4	Work plan for the next period (September 2011 to May 2012)	29

4.1	Planned activities in the next period	29

4.2	Planned meetings and dissemination activities	45

5	Other Issues	45

Appendices to the Interim Technical Implementation Report	46

# Progress Report Summary

## Objectives of the period

The main objectives of this reporting period were to

- collect building datasets representing the national building type classes;

- define constructions and supply systems which are typical for each country;

- elaborate building typology brochures for each country;

- implement additional activities with respect to EPC database analysis, national building stock models and the transferability to non-residential buildings;

- implement the TABULA WebTool;

- involve the National Advisory Groups in this work.

## Achieved results of the period

The main results achieved in the period are:

- an Excel workbook (BuildingTypeMatrix.xls) representing the structure of the residential building stock for the different countries;

- an Excel workbook (TABULA.xls) containing example buildings and supply systems representing the building types of the different countries;

- drafts and final versions of building typology brochures for the different countries;

- a functionally working web tool for displaying the typologies, the datasets and the calculations;

- statistics for the national residential building stock according to typological criteria for different countries.

## Identified problems and corrective actions taken in the period

Although delayed, most of the partners have completed Task 3.1 to 3.4 by now. Since the work of Task 3.5 (additional tasks) is depending on the results of Task 3.1 to 3.4 it is in general some months behind the schedule. For Deliverable D7 (EPC database use) 5 of 9 partners, for D8 (national energy balances) 5 of 9 and partners and for D9 (non-residential buildings) 2 of 5 partners have delivered their contributions (see http://www.building-typology.eu/deliverables.html).

The work on Task 4.1 (WebTool) was more time consuming than expected. In consequence, the publication is delayed (re-scheduled for beginning of November).

The delay of ADEME is due to an internal re-organisation which led to a shortage of staff and time allocation on the project. In the meantime use of non permanent staffing has been achieved and permitted to catch up with the general objectives and time frame of the project - although a slight delay is still experienced.

Partner SOFENA declared that the work on Tasks 3.1.-3.4 will be completed by the end of September. There is a problem with the final agreement and approval on the building types and country typology, which will be overcome after consultations with representatives from the Union of Architects in Bulgaria and the Chember of Engineers in the Investment Design.

The work of the partner MDH has advanced a little but the datasets are still not complete. Unfortunately and despite all efforts by the coordinator, MDH delivered no contribution to this Progress Report. Therefore, no details are available as regards the progress of work and the advancement of working hours.

## Main activities until the end of the action

The activities until the end of the action will be:

- Test and activate the TABULA WebTool (WP4 Task 4.1 and 4.2).

- Few partners: Finalise the collection of building datasets, supply system data and statistics (WP 3 Task 3.1 to 3.4).

- Some partners: Finalise the work on the building typology brochures.

- Few partners: Try to image the energy consumption of the national residential building stocks by use of the respective building typology and statistics and work out the common aspects (WP3 Task 3.5 / subgroup of partners)

- Few partners: Describe ways how to transfer the building typology concept from the residential to the non-residential buildings sector and work out the aspects common for all countries (WP3 Task 3.5 / subgroup of partners)

- Discuss and formulate the general conclusions of the project (WP4 Task 4..3).

- Disseminate the WP3 and WP4 outcome to experts in participating and non-participating countries (WP5). Try to activate further application fields of the TABULA concept.

- Involve the National Advisory Groups in the project according to the NAG concept.

- Implement the different national and international dissemination activities according to the communication plan.

- Perform an international expert workshop on building typologies.

- Perform the last project meeting.

- Elaborate the Final Report.

# Consortium management in the period

The comments of our EACI project officer for the Interim Report were considered in the following way:

- Comment of EACI officer: “There are some notable discrepancies in the number of hours used on this work package by Energy Action - the organization spent 196% of staff hours on WP3, National Building typologies. Requirement: The reasons for this should be reported in more detail to the EACI.” 
Feedback by Energy Action: As the project developed, Energy Action decided to use its own resources for this work. At the contract negotiation stage, Energy Action expected that sub-contractors would be needed to develop web-suited graphics of typical building constructions and heating systems and web-based energy advice applications associated with WP3 and WP4. However the project co-ordinator pointed out that this work was not within the scope of the project for individual partners. At the same time the co-ordinators highlighted that the hours allocated for WP3 for the Irish project were well below those of other partner countries. Thus the allocation for the sub-contract was diverted to WP3 at that stage. This gave Energy Action the option to use a sub-contractor or to use its own in-house resources to complete all tasks for WP3.  As the project developed, Energy Action was satisfied that its in-house experts were best suited to delivering this work. 
Energy Action is currently preparing the budget shift documentation relating to this re-allocation for sub-mission by mid October 2011 approximately. As a result of conducting this work in-house the allocated hours will be increased, in particular for the tasks WP3. As the project has progressed, the volume of work in WP3 has increased from what was envisaged due to the size of the task and the iterative nature of the work. …

- Comment of EACI officer: ”Requirement: The coordinator should clarify when and how the Swedish partner will catch up and when the new edition of the report will be released. It should be also ensured that the findings of this report are well communicated to stakeholders.” 
Feedback by MDH is missing, see comment above.

- Comment of EACI officer: “Recommendation: Involving stakeholders is an important part of the project, so in the upcoming period it should be ensured that the plan is thoroughly implemented and reported on.”
Feedback by Vito: Stakeholder involvement from the scientific community in the partner countries is organized via the National Advisory Groups. The concept for NAG activities as outlined in the draft version  of D17, is and continues to be put into action by all partners individually. Monitoring of these activities is organized and scheduled around the project meetings. Partners fill in a progress template to report NAG activities, and progress is discussed at the meeting itself. Upon that occasion, we have also discussed further possibilities to maximise the NAG concept for stakeholder involvement.

- Comment of EACI officer: “Recommendation: Although there have been some minor additional activities in this respect (input into the BUILD UP newsletter), ideally the interaction should be further intensified.”
Feedback by AEA: After finishing the main work of WP 3 and WP 4 the dissemination of the project will be intensified in the next months including an update of the work (e.g. national brochures) on the build up web portal.

The general consortium management tasks and co-ordination activities in the period were:

- communication and information exchange between partners, mainly via co-ordinator IWU;

- maintenance and updating of the information on the restricted area of the project’s website by IWU (http://www.building-typology.eu/welcomeinternal.html);

- co-ordination of international and national dissemination by WP 5 leaders AEA and ZRMK;

- involvement of National Advisory Groups; concept and tracking of implementation by VITO;

- 1 project meeting; preparation and implementation by IWU / AEA / ZRMK / Vito; organisation by host NAPE:

- 3rd/4th February 2011 in Warsaw / Poland

- co-operation with other projects / programmes:

- presentation of the TABULA project during conferences and workshops (details see below)

- invitation of guests to the meetings

- management and quality assurance by co-ordinator IWU.

# Progress of work plan

## Progress on work packages against initial objectives

| Work Package / Activity | Progress | Role of each partner | Involved third parties | Deviations from the work plan and impact of deviations | Corrective actions taken and results |
| --- | --- | --- | --- | --- | --- |
| WP 1: Management |  |  |  |  |  |
| Task 1.1: Project Management | - progress in line with work programme - | responsible: IWU | - | - | - |
| Task 1.2: General Communication and Project Meetings | - progress in line with work programme - organisation and implementation of project meetings in Darmstadt/Germany, Torino/Italy, Saint-Laurent-du-Var/France, Warsaw/Poland, Ljubljana/Slovenia | responsible: IWU + POLITO + ADEME contributions by all partners | - | - | - |
| Task 1.3: Risk Management Plan | - progress in line with work programme - Risk Management Plan was elaborated (deliverable D1); available at the internal project website: http://www.building-typology.eu/documents/management.html The implementation of the risk management is reported in the minutes of the meetings: http://www.building-typology.eu/downloads/intern/meeting/1/TABULA_1stMeeting_Sep2009_Minutes.pdf http://www.building-typology.eu/downloads/intern/meeting/2/TABULA_2ndMeeting_Feb2010_Minutes.pdf http://www.building-typology.eu/downloads/intern/meeting/3/TABULA_3rdMeeting_Sep2010_Minutes.pdf http://www.building-typology.eu/downloads/intern/meeting/4/TABULA_PM4_Warsaw_Feb2011_Minutes.pdf http://www.building-typology.eu/downloads/intern/meeting/5/TABULA_PM5_Ljubljana_Sep2011_Minutes.pdf | responsible: IWU | - | - | - |
| WP2: Development of a harmonised typology structure |  |  |  |  |  |
| Task 2.1: Analysis of existing approaches and the needs of the target groups | - finalised - results documented in Synthesis Report SR1 (deliverable D3); available at the project website: http://www.building-typology.eu/existent-concepts.html | responsible: IWU contributions by all partners | - | contribution from MDH missing | the missing contribution from Sweden was compensated by more extended searches in non-participating countries MDH declared to catch up on this task; the new information will result in a second edition of SR1 |
| Task 2.2: Definition of the Building Typology Structure | - finalised - common typology structure was elaborated; concept was concretised in Excel workbook “TABULA.xls” and “BuildingTypeMatrix.xls”; draft versions of both files are available at the internal project website: http://www.building-typology.eu/development.html overview of the approach was published in SR1 (see link above) | responsible: IWU contributions by all partners | - | - | - |
| Task 2.3: Agreement on a calculation method | - finalised - common calculation method was elaborated; concept was concretised in Excel workbook “TABULA.xls”; draft version available at internal project website: http://www.building-typology.eu/development.html overview of approach is going to be published in SR1 | responsible: IWU contributions by all partners | - | - | - |
| WP3: National Building Typologies |  |  |  |  |  |
| P01 – IWU – Germany |  |  |  |  |  |
| Task 3.1: Acquisition of building data | - nearly completed - existing German classification system was adapted to the common structure; construction and building type data were defined and entered into TABULA.xls construction pictures were produced an analysis of the dena EPC database was performed twice with the target to improve the empirical derivation of building type data (internal reports: from 10-06-2009 and from 16-04-2010); IWU gave a feedback to dena regarding the necessary improvements of the data collection (missing quantities, quality assurance). Envelope areas as a function of conditioned floor area were derived and used for the definition of average buildings of the national energy balance model (task 3.5). | responsible: IWU | - | analyses of dena EPC database: the number of datasets (n=268 and n=657) was not large enough to derive valid dependences of some interesting quantities (especially calculated as a function of measured consumption); it was decided to repeat the analyses on the basis of a larger number of datasets collected in the meantime | analyses of dena EPC database: dena submitted a new version of the EPC database to IWU in July 2011. A 3rd analysis is now scheduled for October to validate the envelope area data and try to find a better correlation between measured and calculated consumption. |
| Task 3.2: Acquisition of supply system data | - completed - system components as well as heating and hot water system types were defined and entered into TABULA.xls; supply system pictures were produced | responsible: IWU | - | - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | - completed - analyses were carried out by use of a data base including data of about 7.500 German residential buildings which was established by an IWU survey project finished in November 2010 statistical tables have been elaborated | responsible: IWU | - | - | - |
| Task 3.4: Energy balances and energy saving measures | - nearly completed - energy balance calculations for the existing state and the two refurbishment packages were performed “building sheets” were elaborated for all example buildings of the German typology (appendix of the National Building Typology Brochure) draft version of building typology brochure has been distributed to NAG | responsible: IWU | - | - | - |
| Task 3.5: Additional Activities | - progress partly delayed - National energy balance of residential buildings: the required contribution to the report was elaborated; National approach for a typology of non-residential buildings: first ideas have been collected; a draft structure of the report has been developed | responsible: IWU | - | The work on the topic non-residential buildings is delayed since other tasks were more time-consuming than expected (especially Task 4.1). | As soon as the webtool is ready for publishing this work will be concluded. |
| P02 – NOA – Greece |  |  |  |  |  |
| Task 3.1: Acquisition of building data | --completed— The selection of the 24 representative buildings for the Hellenic typology was finalized. Data acquisition for the 6 buildings (pending from the previous reporting period) was completed. Building data was input to the common data structure (TABULA.xls). The Hellenic matrix was finalized Pictures were prepared for all building elements and supplied to the common data structure (Tabula.xls) | responsible: NOA | - | - | - |
| Task 3.2: Acquisition of supply system data | --completed— Τhe most common system types for space and water heating were defined and supplied to the Hellenic typology; these include generation, storage and distribution types. The initial time bands for each system type were refined. Expenditure coefficients for the heat production units in relation to the energy carrier, age and level of maintenance were revised and expressed in terms of the upper calorific value. Energy losses per distribution system and consumption data for auxiliary systems were refined and supplied to the common data structure, | responsible: NOA | - | - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | --completed— Data collection completed. Best estimates were supplied in the cases where data regarding the frequencies of construction elements per building type and age class were not available. In the absence of official data regarding system frequencies, the required information, where necessary, was extracted in collaboration with members of the National Advisory Group from surveys, empirical data or best estimates. The frequencies of building and system types were submitted in tabular form for publication at the project’s website and they are also included in an Appendix in the Scientific Report of NOA. | responsible: NOA | - | - | - |
| Task 3.4: Energy balances and energy saving measures | The most common energy saving interventions on the envelope and systems were described in the common data structure (Tabula.xls) and the corresponding pictures were supplied as necessary. “Standard” and “Advanced” energy saving scenarios were elaborated for each of the 24 buildings included in the Hellenic typology. Energy savings and CO2 emissions reduction were derived for both scenarios using the Tabula calculation tool as well as the National EPA tool (TEE-KENAK). The National Typology Brochure was prepared (in Greek) in the form of a book containing two-page sheets for the 24 buildings of the Hellenic typology along with information on the Hellenic building stock, existing legislation regarding the energy performance assessment of buildings, pros and cons of the most common energy retrofitting interventions and an overview of the existing financial instruments to support them. The first draft of the report (86 pages total) was submitted in May 2011. An electronic version of the Hellenic Brochure (booklet in Greek) can be found at the following link : http://www.energycon.org/tabula/index.html#/home A simple web-based multimedia tool, named eKIA, was prepared on the basis of the TABULA building typology concept. The tool is addressed to home owners wishing to have a first assessment of the energy performance of their building before issuing an EPC. It also offers the possibility to assess the cost effectiveness of energy saving measures on the envelope and systems and their impact on the heating energy consumption of the building. A beta version of eKIA was prepared for demonstration of the concept to the TABULA consortium. The tool is scheduled to be finalised for public use by the end of November. | responsible: NOA | - | - | - |
| Task 3.5: Additional Activities | --completed-- The definition of :”typical” buildings (U-values for envelope components, expenditure coefficients and energy losses for space and water heating systems) was completed. “Typical” building data were supplied to the common data structure (Tabula.xls) Energy balances for the typical buildings corresponding to the 24 classes included in the Hellenic typology were derived using both the Tabula common tool and the national EPA tool (TEE-KENAK). The national EPA tool (TEE-KENAK) was used in order to derive the Energy Balance for the Hellenic residential building sector, Details on the methodology can be found in the1st draft of NOA contribution to D8 report (“National Energy Balance”), submitted in May 2011. The possibility to extend the concept of TABULA to the non-residential building sector was investigated. Available information on tertiary sector building categories was collected. A draft classification of non-residential buildings was proposed. The main findings and conclusions from this task were summarized in the 1st draft of NOA contribution to D9 report (“Non Residential buildings”), submitted in June 2011. | responsible: NOA | - | - | - |
| P03 – ZRMK – Slovenia |  |  |  |  |  |
| Task 3.1: Acquisition of building data | - completed - In the proposal several sources for acquisition of building data were foreseen. As the official national energy certification data base (planned as preferable source of data) hasn’t been implemented yet (an even then it wouldn’t be representative for a while), the reserve plan was activated: The relevant building data were collected from: National real-estate Registry by National Surveying and Mapping Authority of the Republic of Slovenia (includes: the registry of buildings and registry of flats with some additional technical and renovation information), REUS survey – Energy use in households - (REUS from June 2010 is the 2nd annual survey of Sinergija group - public & commercial partnership of 40 partners) – the poll was made by exhaustive questionnaire on energy characteristics of building and user habits (1000 questions on energy-building-HVAC-electricity-renovation-behaviour-habits-values, in a representative sample for Slovenia N=1009, personal interviews – field survey), REUS also joined TABULA NAG classification of whole building stock is based on the National Real-Estate Registry (building type, age). The energy characteristics of the particular class are modelled based on several sources: REUS data, existing database of pilot energy certificates and energy audits; energy saving studies, partner expertise, statistical data - where available. | responsible: ZRMK | - | GI ZRMK had to change from the intention to use a data base of energy performance certificates, as the official national data base hasn’t been established yet. | At the same time there was a voluntary survey of energy efficiency in households planned by a group of stakeholders, ZRMK team joined the advisory group of RES project and vice versa, so that the optimum compatibility of data was established. Later the national registry of real-estate was upgraded with the information on actual energy characteristics of buildings, systems and users habits in residential buildings. Thus we managed to provide even a more comprehensive and statistically reliable data for the TABULA typology. |
| Task 3.2: Acquisition of supply system data | - completed - System types defined The above described approach allowed also to get a more detailed data on supply systems. The national statistics (building registry) only brings a basic information on the energy source, while the REUS data are more precise. | responsible: ZRMK | - | - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | - completed - Frequency of building and system types are available Approach enabled the provision of frequency of particular building type and insight in the frequency of particular systems per building class. In the next steps it is possible to work with: “Real building” with geometrical and thermal characteristics similar to average of the building sample (i.e. statistical relevance of the building sample) – Level 2 “Synthetic buildings” (mainly for the purpose of national energy balance for the residential stock and scenarios) – Level 3 | responsible: ZRMK | - | - | - |
| Task 3.4: Energy balances and energy saving measures | - completed - The analyses of “real building” examples have been carried out and the calculations for different renovation scenarios are on-going. So far, 24 “real building type” examples have been calculated. | responsible: ZRMK | - | - | - |
| Task 3.5: Additional Activities | - completed - National energy balance of residential buildings The analyses of energy balances and energy saving measures have been implemented for “synthetic buildings”, including some scenarios for renovation, taking into account the actual energy characteristics of the building stock. A scenario of renovation measures needed in existing building stock in order to approach as much as possible to 2020 targets in recent EPBD recast based Slovenian building code (PURES-2, 2010) was demonstrated. | responsible: ZRMK | - | - | - |
| P04 – POLITO – Italy |  |  |  |  |  |
| Task 3.1: Acquisition of building data | - completed - the Italian classification system was adapted to the common structure the building types were defined only for the Italian “Middle Climatic Zone” (Italian Climatic Zone E), including about 4250 municipalities of 8100 construction and building type data were defined and entered into TABULA.xls building types were mainly defined through two different databases: the regional database of energy performance certificates (Piedmont Region); a database of fifty real buildings with detailed typology, construction and system data. | responsible: POLITO | - | - | - |
| Task 3.2: Acquisition of supply system data | - completed - components of the space heating and domestic hot water systems were defined and entered into TABULA.xls | responsible: POLITO | - | - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | - nearly completed - statistical tables for the public website are under elaboration | responsible: POLITO | - | - | - |
| Task 3.4: Energy balances and energy saving measures | - completed - scheme and methodology were defined and calculations were performed | responsible: POLITO | - | - | - |
| Task 3.5: Additional Activities | - nearly completed - National energy balance of residential buildings: the building “archetypes” based on statistical analysis has been defined the statistical analysis has been developed revisions are being developed about the energy balance of the “Middle Climatic Zone” | responsible: POLITO | - | - | - |
| P05 – ADEME – France |  |  |  |  |  |
| Task 3.1: Acquisition of building data | Nearly completed - building types defined and entered into TABULA.xls structure - construction pictures produced (although quality definition needs rehearsal) | responsible: ADEME | - | - delay in the feeding up of data in the common excel file structure | - need to involve additional staff |
| Task 3.2: Acquisition of supply system data | completed - Data for supply system available from EPC calculation method entered into TABULA.xls - supply system pictures were produced | responsible: ADEME | - | - delay in the feeding up of data in the common excel file structure | - need to involve additional staff |
| Task 3.3: Acquisition of data on the frequency of building and system types | Nearly completed Analysis of different data sources (census, other specific surveys) were collected and compiled to adapt to TABULA structure for France statistical tables have been produced | responsible: ADEME | - | - | - |
| Task 3.4: Energy balances and energy saving measures | Partly completed, on going - Energy saving measures available - Building sheets elaborated for each building type but discussions with NAG stake holders regarding the final lay out of the Tabula brochure (the energy label used to show the energy performance index should only be produced by a certified auditor which is not the case in the project situation; a derogation is looked after considering the whereabouts of the project) - brochure should be limited to individual houses because 1) in France the owner occupant of a dwelling in a multifamily building has no power to decide alone on retrofits, 2) a specific book on multifamily dwellings (ABC book) has already been issued beginning of 2010 | responsible: ADEME | - | - | - |
| Task 3.5: Additional Activities | Progresse partly delayed to concentrate on completion of previous tasks. - National energy balance of residential building : work started and on going | responsible: ADEME | - | - | - |
| P06 – Energy Action – Ireland |  |  |  |  |  |
| Task 3.1: Acquisition of building data | - nearly completed all work on single family house types has been completed. Work still needs to be completed on Irish multi-family houses/ apartment types and this shoul dbe completed by end October 2011. a classification system for Irish dwellings has been developed in accordance with the common structure (TABULA.xls) based on adaptations of the Irish Dwelling Energy Assessment Method (DEAP) construction types and sub-types have been defined and entered into TABULA.xls. | responsible: Energy Action | - | - | - |
| Task 3.2: Acquisition of supply system data | - substantially completed. some additional heating types may arise when developing the Irish multi-family houses/ apartment types. the defined heating system type data has been entered into TABULA.xls | responsible: Energy Action | - | - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | - progress in line with work programme - the current data available from national statistics has been gathered and has being assessed Major progress has been made on matching TABULA building types to the national EPC database. Detailed results from the national EPC admintration team are expected at end September 2011 which should allow this task to move to completion. | responsible: Energy Action | - | - | - |
| Task 3.4: Energy balances and energy saving measures | - calculation of a national energy balance is not a deliverable for the Irish project. The Irish project will assess where possible the steps require to calculate the national energy balance, though this work may take place outside the TABULA project. | responsible: Energy Action | - | - | - |
| Task 3.5: Additional Activities | - no specific additional activities have been identified for implementation | responsible: Energy Action | - | - | - |
| P07 – VITO – Belgium |  |  |  |  |  |
| Task 3.1: Acquisition of building data | - progress in line with work programme – task has been finalised Inventory of useful statistical data finalised Identification and definition of building types finalised transformation of building type data into common data structure finalised | responsible: VITO | - | - | - |
| Task 3.2: Acquisition of supply system data | - progress in line with work programme – task has been finalised System types are identified Existing classification of technical systems are updated with new technologies Transformation of system type data into common data structure finalised | responsible: VITO | - | - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | - progress in line with work programme – task has been finalised Data from NIS (national institute for statistics) and the regions is gathered These data sources have been used to establish building and system types frequencies | responsible: VITO | - | - | - |
| Task 3.4: Energy balances and energy saving measures | - progress in line with work programme – task has been finalised energy saving measures are defined; concept of building type sheets is established; calculations of typical buildings according to national methods are performed; the national housing typology brochure has been finalised | responsible: VITO | - | - | - |
| Task 3.5: Additional Activities | - progress in line with work programme – task has been finalised National energy balance of residential buildings: the task on national energy balance of residential buildings has been finalised | responsible: VITO | - | - | - |
| P08 – NAPE – Poland |  |  |  |  |  |
| Task 3.1: Acquisition of building data | Almost completed In co-operation with NAG building classification approved – 26 buildings categories All pictures for buildings types ready and entered to the TABULA.xls Construction, building type and data entered to the TABULA.xls | responsible NAPE |  |  |  |
| Task 3.2: Acquisition of supply system data | Finished In co-operation with NAG system categories (for heating and hot water) were defined, approved and entered into TABULA.xls Supply system pictures were developed Data were entered to TABULA.xls | responsible NAPE |  |  |  |
| Task 3.3: Acquisition of data on the frequency of building and system types | Almost finished Available statistical data were assessed An analysis of Build Desk database was performed (about 80 000 buildings) Statistical tables are under development | responsible NAPE | Build Desk – make their building database available for NAPE |  |  |
| Task 3.4: Energy balances and energy saving measures | Progress in the line with work programme: Energy saving measures for all type of buildings already defined and entered to the TABULA.xls Calculations done on the base of real buildings for existing state and the two refurbishment measures were performed Building typology brochures were done for 26 building types. | responsible NAPE |  |  |  |
| Task 3.5: Additional Activities | In progress – partly delayed Statistical data of non-residential buildings were analysed Preliminary structure in co-operation with NAD was defined | responsible NAPE | Build Desk – make their building database available for NAPE | Small delay should be make up till the end of the project |  |
| P09 – AEA – Austria |  |  |  |  |  |
| Task 3.1: Acquisition of building data | -completed- new classification system was adapted to the common structure construction and building type data were defined and are currently entered into TABULA.xls drafts of “building type sheets” to be used in the National Building Typology Brochure were created for two example buildings An analysis of the ZEUS EPC database was performed to verify the building typology and to further develop the approach. | responsible: AEA | Consultancy with NAG |  | - |
| Task 3.2: Acquisition of supply system data | - nearly completed- system components as well as heating and hot water system types were defined and entered into TABULA.xls data are currently revised | responsible: AEA | Consultancy with NAG | - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | -completed- data collection and evaluation is completed statistical tables have been elaborated | responsible: AEA | - | - | - |
| Task 3.4: Energy balances and energy saving measures | -nearly completed- energy balance calculations for the existing state and the two refurbishment packages were performed energy balance calculations are currently compared to national statistical data | responsible: AEA | - | - | - |
| Task 3.5: Additional Activities | - completed- National typology of non- residential buildings: a concept and a classification system has been elaborated; construction and building type data as well as system components and heating/ water system types were defined the required contribution to the report was elaborated Energy certification databases: existing national energy data bases and future possible procedures are presented the required contribution to the report was elaborated | responsible: AEA | - | - | - |
| P10 – SOFENA – Bulgaria |  |  |  |  |  |
| Task 3.1: Acquisition of building data | - the acquision of building data and characteristics completed - building types mainly defined - transformation of building type data into common data structure waiting for further consultancy and agreement with experts from national unions | Responsible: SOFENA | Subcontractor for missing building data | Delay in including datasets in the common structure | Consultancy with experts from the Union of Architects in Bulgaria and The Chamber of Engineers in the Investment Design |
| Task 3.2: Acquisition of supply system data | - system types mainly defined - transformation of system type data into common data structure waiting for final approval from experts from the national unions | Responsible: SOFENA | Subcontractor for missing technical data | Delay in including datasets in the common structure | Consultancy with experts from the Union of Architects in Bulgaria and The Chamber of Engineers in the Investment Design |
| Task 3.3: Acquisition of data on the frequency of building and system types | - progress in line with work programme: - analysis on statistically available data – based on surveys and the results from the last census from February 2011 -concept for accounting partly renovated building typologies elaborated | Responsible: SOFENA | Subcontractor for missing statistical data | - | - |
| Task 3.4: Energy balances and energy saving measures | - nearly completed - - analysis on possible energy saving measures for panel buildings and single and multi-family houses - the design of building typology brochure nearly finalized | Responsible: SOFENA | - | Delay due to dependency on the finalization of the previous 3 tasks | Will be completed in very short term after the finalization of previous activities |
| Task 3.5: Additional Activities | - Basic ideas for a typology for non-residential buildings collected as a result of a survey for the public buildings of Sofia Municipality performed in 2011 -The main typology structure defined, including construction types and systems | Responsible: SOFENA | - | Delay in the finalization of the report | Further efforts will be directed to clarification of all details and elaboration of the Bulgarian methodology and approach |
| P11 – MDH* – Sweden | *) Status from March 2010 – no input by MDH to PR2 |  |  |  |  |
| Task 3.1: Acquisition of building data | - progress delayed - acquisition of panel buildings data and characteristics building types mainly defined in interval for years | Responsible: MDH | Discussion with third parties | Little behind, will catch up | - |
| Task 3.2: Acquisition of supply system data | - progress delayed - analysis on statistically available data working with concept for accounting partly renovated building types | Responsible: MDH | Discussion with third parties | Little behind, will catch up | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | - progress delayed - analysis on statistically available data concept for accounting partly renovated building types in progress | Responsible: MDH | Discussion with third parties | Little behind, will catch up | - |
| Task 3.4: Energy balances and energy saving measures | - progress delayed - list of energy saving measures for each building type | Responsible: MDH | Discussion with third parties | Little behind, will catch up | - |
| Task 3.5: Additional Activities | - task not yet started - | Responsible: MDH |  |  | - |
| P12 – STU-K – Czech Republic |  |  |  |  |  |
| Task 3.1: Acquisition of building data | All necessary building data have been acquired Data are currently being checked, still some mistakes to be removed. | responsible: STU-K | - | - | - |
| Task 3.2: Acquisition of supply system data | All necessary system types data have been acquired Data are currently being checked, still some mistakes to be removed. | responsible: STU-K | - |  | A part of data were delivered by in house consultant |
| Task 3.3: Acquisition of data on the frequency of building and system types | The frequency of buildings has been mapped Sufficient data have been collected. Regarding the data related to the frequency of system types some data are missing and will not be available.The national statistics are providing information about the types of energy primary sources and the quantities of consumed and produced energy but no data about the quantities and efficiencies of heating sources and other parts of the systems. | responsible: STU-K | - | (see comment above) | Only estimations can be made |
| Task 3.4: Energy balances and energy saving measures | - final national energy balance report under elaboration. The work is delayed but already about 80% has been finished. | responsible: STU-K | - | - | Will be soon finished. |
| Task 3.5: Additional Activities | No specific additional activities have been identified for the moment | responsible: STU-K | - | - | - |
| P13 – SBi – Denmark |  |  |  |  |  |
| Task 3.1: Acquisition of building data | - progress in line with work programme - Acquisition of building data done. Transformation of building construction data into common data structure done. | responsible: SBi | - | - | - |
| Task 3.2: Acquisition of supply system data | - progress in line with work programme - Acquisition of supply system data done. Transformation of building supply data into common data structure done. | responsible: SBi | - | - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | - progress in line with work programme - Acquisition of building data done. Transformation of building frequency data into common data structure done. | responsible: SBi | - | - | - |
| Task 3.4: Energy balances and energy saving measures | - progress in line with work programme - Energy balance end energy saving measures done | responsible: SBi | - | - | - |
| Task 3.5: Additional Activities | - progress in line with work programme - National energy balance of residential buildings: the required contribution to the report was elaborated | responsible: SBi | - | - | - |
| WP4: Building Typology WebTool and General Conclusions |  |  |  |  |  |
| Task 4.1: Development of the Building Typology WebTool | The programme specifications, the data structure and the concept for the user interface have been elaborated in accordance with the partners. A concept for the display of the energy balance calculation was implemented in TABULA.xls as a template for the WebTool. A certain number of internet programme tools were checked in order to find adequate solutions for the different requirements of the WebTool (data upload from TABULA.xls, grids with pictures, PDF sheets with calculation features, special charts, …). The data structure of “TABULA.xls” had to be revised several times in order to meet the complex needs of building-system combination and energy balance calculation as well as the requirements of the online database and user interface. A functionally working version of the WebTool was developed according to the concept (see link at internal project website: http://webtool.building-typology.eu/ ). At the moment some minor corrections and improvements are still necessary. A new data import is scheduled for mid October – after this the publication of the WebTool will take place. In order to enable a flexible comparison of input and result data of buildings and systems an additional expert version was elaborated (draft version available at: http://webtool.building-typology.eu/webtool/advanced.html ) | responsible: IWU contributions by all partners | - | progress in line with work programme / but parts of the work were more time-consuming than expected (for impact see comment on Task 3.5 / P01 IWU) special tasks “internet software programming” was realised by new staff member; a subcontractor will not be necessary; | - |
| Task 4.2: Start and test phase of the public Building Typology Webtool | - not yet started - | responsible: IWU contributions by all partners | - | - | - |
| Task 4.3: General Conclusions | - first concept - | responsible: IWU contributions by all partners | - | start of work delayed because of the not yet concluded other tasks | - |
| WP5: Communication and Dissemination |  |  |  |  |  |
| Task 5.1: National Dissemination | - progress in line with work programme - Monitoring of partners’ activities according to the communication plan (see below) is running; The status of dissemination done by the interim report shows that the following main activities were done (summary for all partners): 8 articles, 3 national conferences, 3 poster presentation at fair, 3 E-mail newsletters, 12 national web-pages presenting the project at a national level, 2 brochures, 1 strategic meeting with stakeholders. The current status of national dissemination is available at: http://www.building-typology.eu/communication.html | responsible: ZRMK contributions by all partners | - | - | - |
| Task 5.2: International Dissemination | - progress in line with work programme - a communication plan with a detailed time schedule and different communication phases was worked out in co-operation between AEA, IWU, ZRMK and VITO (deliverable D16) international partners are contacted, information about their status quo regarding typologies is available (for details see Synthesis Report SR1) the first e-mailing action was performed on 28th June 2010 (addressed to 510 energy and buildings experts all over Europe) Due to the interest of institutions from non-participating countries the TABULA team decided to establish the status of “Associated Partner” which includes the following aspects of collaboration: access to project information (concepts, data structure TABULA.xls etc.) invitation to project meetings entry of organisation's name at the TABULA website ("Associated Partners") willingness to create or adapt a national building typology according to the TABULA concept and / or to disseminate the TABULA concept in the respective country and to promote applications in the field of energy advice and building stock monitoring all efforts/expenses for own account (no remuneration / financial contributions from the TABULA consortium) By now the following institutions decided to join TABULA as associated partner: Instituto Valenciano de la Edificación (IVE), Valencia / Spain represented by Begoña Serrano Lanzarote and Leticia Ortega University of Belgrade / Faculty of architecture, Belgrade / Serbia represented by Prof Dr Milica Jovanovic Popovic, dipl.ing.arh. and Doc Dusan Ignjatovic. dipl.ing.arh. There are also intensive contacts to a Scottish expert who also attended a project meeting (Dave Cormack, Communities Analytical Services: Scottish House Condition Survey Team). Further dissemination took place during the following international events IWU: Information about building typologies / TABULA project during workshop of EIE project INTENSE on 18th June 2009 (see: www.intense-energy.eu/uploads/tx_triedownloads/INTENSE_WP3_SV_REPORT.pdf ) IWU: BUILD WITH CaRe Conference 2009: Information about the TABULA objectives during a presentation about comparing energy performance requirements in Oldenburg on 12th November 2009 AEA: general information was given within the EnR regular meeting M46, February 8 – 10th 2010 in Madrid, Spain NOA: a paper (“European Efforts Towards NZEBs and Energy Conservation in Hellenic Buildings”) was presented at the ASHRAE 2011 Winter Conference “Zero Energy Design”, Las Vegas, Nevada, January 29 – February 2, 2011. Overview of Tabula project and main results on the potential energy conservation in the Hellenic building stock. NOA: a paper (“On the Use of Building Typologies to Assess the Energy Performance of the Hellenic Residential Building Stock”) was presented at the 3rd International Conference on Renewable Energy Sources and Energy Efficiency, Nicosia, Cyprus, 19-20 May 2011 (Conference proceedings pp. 364-374). The paper is dedicated to the Tabula project main results with an emphasis on the Hellenic building typologies. During the conference there were contacts of NOA with local stake holders from the University and the Ministry who expressed their interest in TABULA and asked to be included in the list of organizations to receive a regular update on the project progress and outcome, as well as upcoming meetings. NOA: a paper (“Building Typologies as a Tool for Assessing the Energy Performance of Residential Buildings – A Case Study for the Hellenic Building Stock) was submitted for publication in the International Journal Energy and Buildings. SBi: general information given within the Nordic project MECOREN (MEthods and COncepts for sustainable RENovation) project meeting at KTH, Stockholm, 25 march 2010. MECOREN partners: VTT, Finland; KTH, Sweden; SINTEF, Norway; and SBi/AAU, Denmark. VITO: Tabula was introduced to Dutch buildings and policy experts from “AgentschapNL”. Experiences were exchanged and comparisons were made between Tabula and the Dutch building typology - April 13th 2010 in Sittard, Holland SOFENA: Presentation at the International Workshop: Quality Assurance when Retrofitting Energy Efficient Buildings, Sofia., March 10th 2010 SOFENA: Presentation at the International Ecology Congress, Sofia, May 27th 2010 POLITO: A paper (“Definition of building typologies for energy investigations on residential sector by TABULA IEE-project: application to Italian case studies”) was presented at RoomVent 2011 - 12th International conference on air distribution in rooms (Trondheim, Norway, June 2011) POLITO: A paper (“Improving energy modeling of large building stock through the development of archetype buildings”) was submitted and accepted for presentation at next Building Simulation 2011 - 12th International conference of IBPSA (International Building Performance Simulation Association) (Sidney, Australia, November 2011) AEA: Presentation at the international conference: ökosan, September 29th 2011, Graz, The presented poster of the TABULA project was awarded with the 1st prize “best poster of the ökosan conference”. { partners: add further international dissemination activities, if available } | responsible: AEA contributions by all partners | - | - | - |
| Task 5.3 Project Website | - progress in line with work programme - internal and public websites are running main results of WP2 were processed to web information (see: http://www.building-typology.eu/existent-concepts/typologies-examples.html and following pages) | responsible: IWU contributions by all partners | - | publication of WP3 results and online webtool is delayed since final versions of deliverables are not yet available | - |
| WP6: IEE Dissemination Activities |  |  |  |  |  |
| Task 6.1: Contribution to IEE online information system | project fact sheet was elaborated and updated | responsible: IWU | - | - | - |
| Task 6.2: Contribution to the development of additional information material | - | responsible: IWU | - | - | - |
| Task 6.3: Contribution to EU dissemination events | EACI Project Slides were elaborated and updated | responsible: IWU | - | - | - |
| Task 6.4: Contribution to CA EPBD and BuildUp | CA EPBD: overview of TABULA objectives and planned activities during EPBD CA meeting in Berlin (June 2009) project information on BuildUp website: http://www.buildup.eu/publications/8046 (short project information) http://www.buildup.eu/publications/9927 (information about Synthesis Report SR1 http://www.buildup.eu/sites/default/files/newsletter/Newsletter_no_13.pdf (BuildUp Newsletter July 2010) | responsible: IWU / AEA | - | - | information will be posted at Build Up website / newsletter after publication of national building typologies / webtool at the TABULA website (Nov 2011) |

## Deviations (advancement of working hours)

Deviations from the project work plan, the impact of these deviations and the corrective actions are described directly in the table of chapter 3.1.

The comments on deviations concerning the advancement of working hours in Appendix Table 2 are:

- IWU (P01): The work during Activity 4.1 turned out to be more time-consuming than expected. The workbook “TABULA.xls” had to be restructured several times in order to meet the complex needs of building-system combinations and energy balance calculation as well as the requirements of the online database and user interface. Apart from this some of the programming work which was originally planned to be subcontracted could be done by own staff (new staff member) which allowed a higher flexibility of development. 
As regards the internet programming the search and test of tools and settings which fit all needs (e.g. flexible grids that quickly load pictures, online calculation by PDF sheets, …) was a lot more time-consuming than expected. 
As an additional task an expert version of the tool was developed which now enables a flexible choice of building and system datasets (by use of filter functions) and an online comparison of buildings from different countries (including the datasets of average buildings, as far as already available). This additional feature will supplement the cross-country comparison planned in task 4.3 by the possibility for expert users to make their own comparisons of interesting quantities with customised selections of buildings / systems. It especially aims at the experts involved in EPBD implementation on European level and will therefore be communicated in the Build Up web portal.

- POLITO (P04): The POLITO scientist in charge decided to increase of one researcher the internal TABULA team to assure the expected result. The assigned budget does not have any change due to this effort increase.

- Ademe (P05): An internal re-organisation in Ademe had led to a shortage of staff and time allocation on the project. In the meantime use of non permanent staffing has been achieved and permitted to catch up with the general objectives and time frame of the project. Nevertheless, working hour allocation is still not as expected.

- Energy Action (P06): see explanation in chapter 2

- AEA (P09): AEA had to spend more hours than originally planned in the contract planning phase. In the first phase the TABULA project team changed resulting in some inefficiencies concerning the continuation of the progress of the project. The working hours for WP3 were heavily underestimated at the beginning of the project (by the old project management), for this reason more hours than expected had to be spent to obtain the expected project results. Furthermore to be able to implement the national energy balances approach significant work hours had also to be foreseen.

## Interim review of deliverables

The deliverables are listed in the Appendix Table 1. They have been elaborated and published in compliance with the work plan (grant agreement Annex I).

## Interim review of performance indicators

| Performance Indicators from the TABULA Contract | Impacts of the action achieved so far |
| --- | --- |
| Specific Objectives | Result Indicators | Target (quantification) of success |  |
| develop a harmonised building typology structure | agreement on a common structure | utilisation of the typology structure is possible for all participating countries | target has been attained |
| fill the typology structure with data on a national level | level of detail: number of building types completeness of data: sub-typologies of supply systems and building elements available information on frequencies of building types and heat supply systems available | Level of Detail: 20 building types per participating country (on average) Completeness: sub-typologies available for all participating countries basic information on frequencies available: Maybe not for each single type separately, but sufficiently detailed, distinguishing at least 6 groups of building types per country, e.g. 3 construction periods x 2 building sizes (single or multi-family houses) | on-going work / the targets regarding level of detail and completeness will in general be attained by the partners (see table below); for two partners the progress is not sufficient at the moment |
| provide a webtool with typology data and demonstration application | public availability of data demonstration calculation works | for all participating countries: data available for all national building types demonstration calculation works for the available building types | - to be checked in November 2011 - |
| update the national EPBD implementing bodies on concrete outcomes of the project | presentation at sessions of the CA EPBD, CA ESD or equivalent | number of presentations of outcomes: 2 | presentation at EPBD CA meeting in June 2009 |
| early, or preliminary, utilisation of the national building typologies for evaluation and forecasting the impact of policies and measures | number of applications in the framework of policies and measures of the participating countries | number of actual applications: 4 number of expressions of interest: 7 | at the moment 5 applications: building typologies based on the TABULA concept were used to assess the energy consumption and the energy saving potentials of the residential building stocks in Belgium, Denmark, Germany, Greece, Italy |
| as above | As above, but for non-participating countries | number of actual applications: 2 number of expressions of interest: 4 | experts from Serbia (TABULA associated partner) expressed their interest |
| expansion to other countries | finding typology caretakers from non-participating countries who will provide and update the respective national typology data | number of caretakers: 2 | Until now institutions from Spain and from Serbia decided to join the TABULA consortium as associated partners and to elaborate their own building typologies using the TABULA scheme (see above, progress of work in Task 5.2). |
| Strategic Objectives | Impact Indicators: | Target (quantification) of success: |  |
| methodology adopted at national level in EU Member States | number of EU countries adopting the methodology | between 33% to 50% of EU Member States adopt the methodology, or a nationally adapted derivative thereof, within their national approach to maximising EPBD impact | - to be checked at a later stage - Clarification regarding the quoted target: Of course, not the member states themselves can adopt the methodology but scientist can use building typologies for assessing and forecasting the energy consumption of the respective national building stocks. |
| improved knowledge of the state-of-the-art of EU building stock in both the residential and non-residential sectors | EU countries have a detailed understanding of the current state of the building stock | project methodology and outcomes referenced in sectorial studies, statistical analyses and/or standardisation activities | - to be checked at a later stage - |
|  |  | Remark: quantification of the strategic success will realistically only be possible after the end of the project period. But because of the test phase of the project webtool there will be some chance to already find applicants and caretakers within the project period |  |

Number of datasets in TABULA.xls

| Code_Country | AT | BE | BG | CZ | DE | DK | FR | GR | IE | IT | PL | SE | SI |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tab.Building.Constr | 95 | 53 | 0 | 58 | 88 | 244 | 90 | 205 | 64 | 76 | 110 | 50 | 59 |
| Tab.Building.Measure | 35 | 18 | 0 | 29 | 44 | 23 | 25 | 34 | 31 | 42 | 20 | 5 | 12 |
| Tab.System.HG | 31 | 33 | 0 | 19 | 43 | 33 | 18 | 80 | 12 | 24 | 24 | 12 | 1 |
| Tab.System.HS | 9 | 4 | 0 | 4 | 4 | 11 | 1 | 4 | 0 | 9 | 4 | 7 | 1 |
| Tab.System.HD | 5 | 8 | 0 | 6 | 10 | 9 | 4 | 39 | 4 | 24 | 4 | 2 | 1 |
| Tab.System.HA | 3 | 5 | 0 | 3 | 3 | 5 | 3 | 4 | 4 | 10 | 2 | 6 | 1 |
| Tab.System.WG | 20 | 18 | 0 | 18 | 47 | 27 | 22 | 62 | 10 | 27 | 13 | 10 | 1 |
| Tab.System.WS | 10 | 8 | 0 | 11 | 11 | 4 | 3 | 6 | 8 | 15 | 11 | 2 | 1 |
| Tab.System.WD | 5 | 10 | 0 | 8 | 11 | 2 | 5 | 25 | 4 | 16 | 4 | 1 | 1 |
| Tab.System.WA | 4 | 6 | 0 | 5 | 9 | 3 | 5 | 9 | 0 | 13 | 5 | 0 | 1 |
| Tab.System.H | 14 | 8 | 0 | 8 | 29 | 21 | 21 | 66 | 19 | 76 | 19 | 2 | 1 |
| Tab.System.W | 16 | 13 | 0 | 11 | 32 | 15 | 26 | 28 | 17 | 55 | 11 | 0 | 1 |
| Tab.System.Vent | 4 | 4 | 0 | 2 | 5 | 6 | 5 | 0 | 2 | 1 | 3 | 0 | 1 |
| Tab.Type.Building | 54 | 29 | 0 | 26 | 44 | 27 | 61 | 24 | 29 | 32 | 26 | 2 | 20 |
| Tab.Building | 54 | 29 | 0 | 28 | 44 | 54 | 61 | 48 | 29 | 32 | 26 | 2 | 20 |
| Tab.Type.System | 40 | 14 | 0 | 4 | 31 | 27 | 41 | 58 | 19 | 64 | 12 | 0 | 1 |
| Tab.System.Measure | 24 | 10 | 0 | 2 | 8 | 5 | 26 | 37 | 18 | 34 | 7 | 0 | 1 |
| Calc.Building.Set | 154 | 81 | 0 | 78 | 132 | 162 | 183 | 95 | 87 | 84 | 78 | 0 | 3 |

Status on 9th September

In the meantime progress has been made, especially by ZRMK (SI) and STU-K (CZ). 
The current status is available in [TABULA.xls]Tab.Info.Country (http://www.building-typology.eu/downloads/intern/development/TABULA-xls.zip)

# Work plan for the next period (September 2011 to May 2012)

## Planned activities in the next period

| Work Package / Activity | Planned tasks until the end of the project | Role of each partner | Deliverables | Due dates |
| --- | --- | --- | --- | --- |
| WP 1: Management |  |  |  |  |
| Task 1.1: Project Management | co-ordination of activities, information flow, reporting to EACI | responsible: IWU | - | - |
| Task 1.2: General Communication and Project Meetings | organisation and implementation the final project meeting | responsible: IWU + AEA (host) contributions by all partners | - | - |
| Task 1.3 Risk Management Plan | checks according to the Risk Management Plan (see Appendix Table 1) | responsible: IWU | - see below - | - |
| Deliverable D1 (Tasks 1.3) | finalised (see Appendix Table 1) |  | D1: Risk Management Plan | Sep 2009 |
| Deliverable D2 (WP2, WP3, WP4, WP5) | first concept of the final report |  | D2: Final Report (result oriented) | Jul 2012 |
| WP2: Development of a harmonised typology structure |  |  |  |  |
| Task 2.1: Analysis of existing approaches and the needs of the target groups | - task concluded - | responsible: IWU contributions by all partners |  |  |
| Task 2.2: Definition of the Building Typology Structure | - task concluded - | responsible: IWU contributions by all partners |  |  |
| Task 2.3: Agreement on a calculation method | - task concluded - | responsible: IWU contributions by all partners |  |  |
| Deliverable D3 (Tasks 2.1 to 2.3) |  |  | D3: Synthesis Report SR1 | May 2010 |
| WP3: National Building Typologies |  |  |  |  |
| P01 – IWU – Germany |  |  |  |  |
| Task 3.1: Acquisition of building data | analyse EPC database of dena and consider results, if possible (average envelope areas for update of average buildings data; relation of measured to calculated consumption, if possible) | responsible: IWU | - see below - | - |
| Task 3.2: Acquisition of supply system data | - none - | responsible: IWU | - see below - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | - none - | responsible: IWU | - see below - | - |
| Task 3.4: Energy balances and energy saving measures | finalisation and publication of building typology brochure | responsible: IWU | - see below - | - |
| Task 3.5: Additional Activities | continue the additional national activity “national approach for a typology of non-residential buildings” | responsible: IWU | - see below - | - |
| Deliverable D4 (Tasks 3.1 to 3.2) | - task concluded - | responsible: IWU | D4.1 National Building Typology Datasets | May 2011 |
| Deliverable D5 (Tasks 3.1 to 3.4) | - task nearly concluded - revision of final draft after feedback by NAG | responsible: IWU | D5.1 National Typology Brochure | May 2011 |
| Deliverable D6 (Tasks 3.1 to 3.5) | elaborate and publish the scientific report, showing the approaches and results of the national activities during WP3 | responsible: IWU | D6.1 Scientific Report on National Typology Project | May 2011 (shift to Aug 2011) |
| Deliverable D7 (Tasks 3.1 to 3.3) | continue and finalise the work on the joint documentation of experiences and recommendations regarding the use of energy certificate databases for building stock monitoring | responsible: IWU contributions by all concerned partners | D7 Report: Guideline Energy Certificate Database Use for Building Typologies | May 2011 (shift to Aug 2011) |
| Deliverable D8 (Task 3.5) | - task concluded - | responsible: IWU contributions by all concerned partners | D8 Report: Contribution of Building Typologies to National Energy Balances | May 2011 (shift to Aug 2011) |
| Deliverable D9 (Task 3.5) | continue and finalise the work on the joint documentation of experiences and recommendations regarding non-residential building typologies | responsible: IWU contributions by all concerned partners | D9 Report: Simplifying Energy Assessment of Non-Residential Buildings by use of Building Typologies | May 2011 (shift to Aug 2011) |
| P02 – NOA – Greece |  |  |  |  |
| Task 3.1: Acquisition of building data | Task concluded-- | responsible: NOA | - see below - | - |
| Task 3.2: Acquisition of supply system data | Task concluded-- | responsible: NOA | - see below - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | Task concluded-- | responsible: NOA | - see below - | - |
| Task 3.4: Energy balances and energy saving measures | Elaboration and finalization of the Scientific Report. Finalization and publication of the web-based multimedia tool eKIA. Upload in NOA’s website for public use, Investigation of the possibility to upload eKIA in the websites of the Ministry or the Technical Chamber of Greece for a wider national dissemination | responsible: NOA | - see below - | - |
| Task 3.5: Additional Activities | a) National Energy Balance of Residential Buildings: Minor revision and finalization of the report b) National Approach for Non-Residential Building typologies: Task concluded | responsible: NOA | - see below - | - |
| Deliverable D4 (Tasks 3.1 to 3.2) | Minor revision and finalisation of the National Typology Datasets | responsible: NOA | D4.2 National Building Typology Datasets | May 2011 |
| Deliverable D5 (Tasks 3.1 to 3.4) | Minor revision and finalisation of the Hellenic “National Typology Brochure” (deliverable D5, in Greek). | responsible: NOA | D5.2 National Typology Brochure | May 2011 |
| Deliverable D6 (Tasks 3.1 to 3.5) | Elaboration and finalization of the 1st draft of the National Scientific Report describing the approach and results of the national activities in the framework of WP3. | responsible: NOA | D6.2 Scientific Report on National Typology Project | May 2011 (shift to Aug 2011) |
| Deliverable D7 (Tasks 3.1 to 3.3) | N/A | responsible: IWU contributions by NOA | D7 Report: Guideline Energy Certificate Database Use for Building Typologies | May 2011 (shift to Aug 2011) |
| Deliverable D8 (Task 3.5) | Task concluded | responsible: IWU contributions by NOA | D8 Report: Contribution of Building Typologies to National Energy Balances | May 2011 (shift to Aug 2011) |
| Deliverable D9 (Task 3.5) | Task concluded | responsible: IWU contributions by NOA | D9 Report: Simplifying Energy Assessment of Non-Residential Buildings by use of Building Typologies | May 2011 (shift to Aug 2011) |
| P03 – ZRMK – Slovenia |  |  |  |  |
| Task 3.1: Acquisition of building data | -none- | responsible: ZRMK | - see below - | - |
| Task 3.2: Acquisition of supply system data | -none- | responsible: ZRMK | - see below - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | -none- | responsible: ZRMK | - see below - | - |
| Task 3.4: Energy balances and energy saving measures | finalisation and publication of building typology brochure | responsible: ZRMK | - see below - | - |
| Task 3.5: Additional Activities | reporting of National Energy Balance of Residential Buildings aiming at low energy restoration for 202020 targets. | responsible: ZRMK | - see below - | - |
| Deliverable D4 (Tasks 3.1 to 3.2) | concluded | responsible: ZRMK | D4.3 National Building Typology Datasets | May 2011 |
| Deliverable D5 (Tasks 3.1 to 3.4) | nearly concluded: finalizing the brochure and printing | responsible: ZRMK | D5.3 National Typology Brochure | May 2011 |
| Deliverable D6 (Tasks 3.1 to 3.5) | nearly concluded: elaborate and publish the scientific report, showing the approaches and results of the national activities during WP3 | responsible: ZRMK | D6.3 Scientific Report on National Typology Project | May 2011 (shift to Aug 2011) |
| Deliverable D7 (Tasks 3.1 to 3.3) | - no contributions foreseen - | responsible: IWU | D7 Report: Guideline Energy Certificate Database Use for Building Typologies | May 2011 (shift to Aug 2011) |
| Deliverable D8 (Task 3.5) | nearly concluded: finalizing the report showing Slovenian approach to National Energy Balances using Typologies | responsible: IWU contributions by ZRMK | D8 Report: Contribution of Building Typologies to National Energy Balances | May 2011 (shift to Aug 2011) |
| Deliverable D9 (Task 3.5) | - no contributions foreseen - | - | - | - |
| P04 – POLITO – Italy |  |  |  |  |
| Task 3.1: Acquisition of building data | - concluded - | responsible: POLITO | - see below - | - |
| Task 3.2: Acquisition of supply system data | - concluded - | responsible: POLITO | - see below - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | finalisation of the statistical tables for the public website | responsible: POLITO | - see below - | - |
| Task 3.4: Energy balances and energy saving measures | - concluded - | responsible: POLITO | - see below - | - |
| Task 3.5: Additional Activities | National Energy Balance of Residential Buildings: finalisation of the energy balance with specifications on the “Middle Climatic Zone” Energy assessment of Non-Residential Buildings: survey on existing data about building types and benchmark values for school buildings | responsible: POLITO | - see below - | - |
| Deliverable D4 (Tasks 3.1 to 3.2) | - concluded - | responsible: POLITO | D4.4 National Building Typology Datasets | May 2011 |
| Deliverable D5 (Tasks 3.1 to 3.4) | - concluded - | responsible: POLITO | D5.4 National Typology Brochure | May 2011 |
| Deliverable D6 (Tasks 3.1 to 3.5) | advance the work and publish a scientific report, showing the approaches and results of the national activities during WP3 | responsible: POLITO | D6.4 Scientific Report on National Typology Project | May 2011 (shift to Aug 2011) |
| Deliverable D7 (Tasks 3.1 to 3.3) | - concluded – In particular, experiences of the Italian National Energy Agency (ENEA), and of Piedmont Region have been analysed. | responsible: IWU contributions by POLITO | D7 Report: Guideline Energy Certificate Database Use for Building Typologies | May 2011 (shift to Aug 2011) |
| Deliverable D8 (Task 3.5) | the report is nearly concluded, some specifications will be done about the energy balance of the “Middle Climatic Zone” | responsible: IWU contributions by POLITO | D8 Report: Contribution of Building Typologies to National Energy Balances | May 2011 (shift to Aug 2011) |
| Deliverable D9 (Task 3.5) | survey on existing data about building types and benchmark values for school buildings | responsible: IWU contributions by POLITO | D9 Report: Simplifying Energy Assessment of Non-Residential Buildings by use of Building Typologies | May 2011 (shift to Aug 2011) |
| P05 – ADEME – France |  |  |  |  |
| Task 3.1: Acquisition of building data | Consistency checking of input data Improvement of pictures quality | responsible: ADEME | - see below - | - |
| Task 3.2: Acquisition of supply system data | none | responsible: ADEME | - see below - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | none | responsible: ADEME | - see below - | - |
| Task 3.4: Energy balances and energy saving measures | finalisation and publication of building typology brochure | responsible: ADEME | - see below - | - |
| Task 3.5: Additional Activities | Finalize national energy balance for residential building sector, analysis and comparisons with other sources or studies | responsible: ADEME | - see below - | - |
| Deliverable D4 (Tasks 3.1 to 3.2) |  | responsible: ADEME | D4.5 National Building Typology Datasets | May 2011 |
| Deliverable D5 (Tasks 3.1 to 3.4) | - nearly concluded - revision of final draft after feedback by NAG | responsible: ADEME | D5.5 National Typology Brochure | May 2011 |
| Deliverable D6 (Tasks 3.1 to 3.5) | elaborate and publish the scientific report, showing the approaches and results of the national activities during WP3 | responsible: ADEME | D6.5 Scientific Report on National Typology Project | May 2011 (shift to Aug 2011) |
| Deliverable D7 (Tasks 3.1 to 3.3) | Contribution delivered | responsible: IWU contributions by ADEME | D7 Report: Guideline Energy Certificate Database Use for Building Typologies | May 2011 (shift to Aug 2011) |
| Deliverable D8 (Task 3.5) | Finalise contribution | responsible: IWU contributions by ADEME | D8 Report: Contribution of Building Typologies to National Energy Balances | May 2011 (shift to Aug 2011) |
| Deliverable D9 (Task 3.5) | - no contributions foreseen - | - | - | - |
| P06 – Energy Action – Ireland |  |  |  |  |
| Task 3.1: Acquisition of building data | add in Irish multi-family and apartment types | responsible: ENERGY ACTION | - see below - | - |
| Task 3.2: Acquisition of supply system data | refine existing heating systems types if required for multi-family and apartment types | responsible: ENERGY ACTION | - see below - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | once the data becomes available from the national EPC data, complete the task on frequency and building types | responsible: ENERGY ACTION | - see below - | - |
| Task 3.4: Energy balances and energy saving measures | finales and complete the building typology brochures | responsible: ENERGY ACTION | - see below - | - |
| Task 3.5: Additional Activities | develop an outline of the proposed approach required to create a TABULA-based national energy balance within the scientific report | responsible: ENERGY ACTION | - see below - | - |
| Deliverable D4 (Tasks 3.1 to 3.2) | completed except for Irish multi-family and apartment types | responsible: ENERGY ACTION | D4.6 National Building Typology Datasets | May 2011 |
| Deliverable D5 (Tasks 3.1 to 3.4) | Finalise the work on the National Typology Brochure | responsible: ENERGY ACTION | D5.6 National Typology Brochure | May 2011 |
| Deliverable D6 (Tasks 3.1 to 3.5) | Develop the scientific report, showing the approaches and results of the national activities during WP3 | responsible: ENERGY ACTION | D6.6 Scientific Report on National Typology Project | May 2011 (shift to Aug 2011) |
| Deliverable D7 (Tasks 3.1 to 3.3) | Input will be provided during October 2011. | responsible: IWU contributions by ENERGY ACTION | D7 Report: Guideline Energy Certificate Database Use for Building Typologies | May 2011 (shift to Aug 2011) |
| Deliverable D8 (Task 3.5) | Energy Action is not formally committed to this task. Where possible, Energy Action will contribute to the development of this report from an Irish perspective | responsible: IWU contributions by ENERGY ACTION | D8 Report: Contribution of Building Typologies to National Energy Balances | May 2011 (shift to Aug 2011) |
| Deliverable D9 (Task 3.5) | none | responsible: IWU | D9 Report: Simplifying Energy Assessment of Non-Residential Buildings by use of Building Typologies | May 2011 (shift to Aug 2011) |
| P07 – VITO – Belgium |  |  |  |  |
| Task 3.1: Acquisition of building data | - none - | responsible: VITO | - see below - | - |
| Task 3.2: Acquisition of supply system data | - none - | responsible: VITO | - see below - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | - none - | responsible: VITO | - see below - | - |
| Task 3.4: Energy balances and energy saving measures | publication of building typology brochure | responsible: VITO | - see below - | - |
| Task 3.5: Additional Activities | - none - | responsible: VITO | - see below - | - |
| Deliverable D4 (Tasks 3.1 to 3.2) | VITO is finalising the work on National Typology Datasets: the statistical stable still need to be delivered | responsible: VITO | D4.7 National Building Typology Datasets | May 2011 |
| Deliverable D5 (Tasks 3.1 to 3.4) | The National Typology Brochure has been finalised | responsible: VITO | D5.7 National Typology Brochure | May 2011 |
| Deliverable D6 (Tasks 3.1 to 3.5) | The scientific report has been finalised | responsible: VITO | D6.7 Scientific Report on National Typology Project | May 2011 (shift to Aug 2011) |
| Deliverable D7 (Tasks 3.1 to 3.3) | The VITO contribution to D8 is under preparation and will be finalised in October 2011 | responsible: IWU contributions by VITO | D7 Report: Guideline Energy Certificate Database Use for Building Typologies | May 2011 (shift to Aug 2011) |
| Deliverable D8 (Task 3.5) | The VITO contribution to D8 has been finalised | responsible: IWU contributions by VITO | D8 Report: Contribution of Building Typologies to National Energy Balances | May 2011 (shift to Aug 2011) |
| Deliverable D9 (Task 3.5) | - no contributions foreseen - | - | - | - |
| P08 – NAPE – Poland |  |  |  |  |
| Task 3.1: Acquisition of building data | -none | responsible: NAPE | - see below - | - |
| Task 3.2: Acquisition of supply system data | -none | responsible: NAPE | - see below - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | -none | responsible: NAPE | - see below - | - |
| Task 3.4: Energy balances and energy saving measures | publication of budiling typologvy brochure | responsible: NAPE | - see below - | - |
| Task 3.5: Additional Activities | National typology for non-residential buildings - school - continuation of activities | responsible: NAPE | - see below - | - |
| Deliverable D4 (Tasks 3.1 to 3.2) | finished | responsible: NAPE | D4.8 National Building Typology Datasets | May 2011 |
| Deliverable D5 (Tasks 3.1 to 3.4) | Almost finished – in revision by NAG | responsible: NAPE | D5.8 National Typology Brochure | May 2011 |
| Deliverable D6 (Tasks 3.1 to 3.5) | Under development – delayed – ready till mid of November | responsible: NAPE | D6.8 Scientific Report on National Typology Project | May 2011 (shift to Aug 2011) |
| Deliverable D7 (Tasks 3.1 to 3.3) | In progress | responsible: IWU contributions by NAPE | D7 Report: Guideline Energy Certificate Database Use for Building Typologies | May 2011 (shift to Aug 2011) |
| Deliverable D8 (Task 3.5) | - no contributions foreseen - | - | - | - |
| Deliverable D9 (Task 3.5) | Continuation and finalisation of the work - apply the TABULA.xls concept to schools buidlings | responsible: IWU contributions by NAPE | D9 Report: Simplifying Energy Assessment of Non-Residential Buildings by use of Building Typologies | May 2011 (shift to Aug 2011) |
| P09 – AEA – Austria |  |  |  |  |
| Task 3.1: Acquisition of building data | -none- | responsible: AEA | - see below - | - |
| Task 3.2: Acquisition of supply system data | -nearly concluded- revision of data | responsible: AEA | - see below - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | -none- | responsible: AEA | - see below - | - |
| Task 3.4: Energy balances and energy saving measures | nearly concluded- Compare energy blance calculations to national statistical data | responsible: AEA | - see below - | - |
| Task 3.5: Additional Activities | - none- | responsible: AEA | - see below - | - |
| Deliverable D4 (Tasks 3.1 to 3.2) | -nearly concluded- revision of final data inputs | responsible: AEA | D4.9 National Building Typology Datasets | May 2011 |
| Deliverable D5 (Tasks 3.1 to 3.4) | -none- National brochure was published on the AEA website in June 2011. | responsible: AEA | D5.9 National Typology Brochure | May 2011 |
| Deliverable D6 (Tasks 3.1 to 3.5) | -nearly concluded- finish and publish the scientific report, showing the approaches and results of the national activities during WP3 | responsible: AEA | D6.9 Scientific Report on National Typology Project | May 2011 (shift to Aug 2011) |
| Deliverable D7 (Tasks 3.1 to 3.3) | - none- The joint documentation of experiences and recommendations regarding the use of energy certificate databases for building stock monitoring was finalised. | responsible: IWU contributions by AEA | D7 Report: Guideline Energy Certificate Database Use for Building Typologies | May 2011 (shift to Aug 2011) |
| Deliverable D8 (Task 3.5) | - no contributions foreseen - | - | - | - |
| Deliverable D9 (Task 3.5) | -none- The joint documentation of experiences and recommendations regarding non-residential building typologies was finalised. | responsible: IWU contributions by AEA | D9 Report: Simplifying Energy Assessment of Non-Residential Buildings by use of Building Typologies | May 2011 (shift to Aug 2011) |
| P10 – SOFENA – Bulgaria |  |  |  |  |
| Task 3.1: Acquisition of building data | Final agreement on the building typology implement a consistent national building typology in TABULA.xls | responsible: SOFENA | - see below - | - |
| Task 3.2: Acquisition of supply system data | implement a consistent national system typology in TABULA.xls | responsible: SOFENA | - see below - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | implement data on the frequency of building and system types in TABULA.xls | responsible: SOFENA | - see below - | - |
| Task 3.4: Energy balances and energy saving measures | perform showcase calculations for some example building types determine the energy savings achieved by typical and advanced measures | responsible: SOFENA | - see below - | - |
| Task 3.5: Additional Activities | elaborate a concept for the additional national activity foreseen in the work programme: National Approach for a Typology of Non-Residential Buildings | responsible: SOFENA | - see below - | - |
| Deliverable D4 (Tasks 3.1 to 3.2) | elaborate a first version of National Typology Datasets | responsible: SOFENA | D4.10 National Building Typology Datasets | May 2011 |
| Deliverable D5 (Tasks 3.1 to 3.4) | elaborate a first draft of the National Typology Brochure | responsible: SOFENA | D5.10 National Typology Brochure | May 2011 |
| Deliverable D6 (Tasks 3.1 to 3.5) | elaborate the concept for a scientific report, showing the approaches and results of the national activities during WP3 | responsible: SOFENA | D6.10 Scientific Report on National Typology Project | May 2011 (shift to Aug 2011) |
| Deliverable D7 (Tasks 3.1 to 3.3) | agree on a concept for the joint documentation of experiences and recommendations regarding the use of energy certificate databases for building stock monitoring | responsible: IWU contributions by SOFENA | D7 Report: Guideline Energy Certificate Database Use for Building Typologies | May 2011 (shift to Aug 2011) |
| Deliverable D8 (Task 3.5) | - no contributions foreseen - | responsible: IWU | - | - |
| Deliverable D9 (Task 3.5) | agree on a concept for the joint documentation of experiences and recommendations regarding non-residential building typologies | responsible: IWU contributions by SOFENA | D9 Report: Simplifying Energy Assessment of Non-Residential Buildings by use of Building Typologies | May 2011 (shift to Aug 2011) |
| P11 – MDH* – Sweden | *) Status from March 2010 – no input by MDH to PR2 |  |  |  |
| Task 3.1: Acquisition of building data | further collection of national building type data and transform into the common data structure implement a consistent national building typology in TABULA.xls | responsible: MDH | - see below - | - |
| Task 3.2: Acquisition of supply system data | further collection of supply system data and transform them into the common data structure implement a consistent national system typology in TABULA.xls | responsible: MDH | - see below - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | collect further statistical data and give an overview process it by use of the agreed common statistics structure analysis on partly renovation of the building stock in Bulgaria | responsible: MDH | - see below - | - |
| Task 3.4: Energy balances and energy saving measures | perform showcase calculations for some example building types determine the energy savings achieved by typical and advanced measures | responsible: MDH | - see below - | - |
| Task 3.5: Additional Activities | elaborate a concept for the additional national activities foreseen in the work programme: National Energy Balance of Residential Buildings | responsible: MDH | - see below - | - |
| Deliverable D4 (Tasks 3.1 to 3.2) | elaborate a first version of National Typology Datasets | responsible: MDH | D4.11 National Building Typology Datasets | May 2011 |
| Deliverable D5 (Tasks 3.1 to 3.4) | elaborate a first draft of the National Typology Brochure | responsible: MDH | D5.11 National Typology Brochure | May 2011 |
| Deliverable D6 (Tasks 3.1 to 3.5) | elaborate the concept for a scientific report, showing the approaches and results of the national activities | responsible: MDH | D6.11 Scientific Report on National Typology Project | May 2011 (shift to Aug 2011) |
| Deliverable D7 (Tasks 3.1 to 3.3) | agree on a concept for the joint documentation of experiences and recommendations regarding the use of energy certificate databases for building stock monitoring | responsible: IWU contributions by MDH | D7 Report: Guideline Energy Certificate Database Use for Building Typologies | May 2011 (shift to Aug 2011) |
| Deliverable D8 (Task 3.5) | summarizing the additional activities on contribution of national typologies to the National Energy balances, comments on common EU approach | responsible: IWU contributions by MDH | D8 Report: Contribution of Building Typologies to National Energy Balances | May 2011 (shift to Aug 2011) |
| Deliverable D9 (Task 3.5) | - no contributions foreseen - | - | - | - |
| P12 – STU-K – Czech Republic |  |  |  |  |
| Task 3.1: Acquisition of building data | -none | responsible: STU-K | - see below - | - |
| Task 3.2: Acquisition of supply system data | -finalize the checking of acquired supply systems data -complete the pictures of the supply systems - upload the final version of datasets | responsible: STU-K | - see below - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | -finalize the analysis of national statistical data, find a suitable way to overbridge the gaps in acquired data | responsible: STU-K | - see below - | - |
| Task 3.4: Energy balances and energy saving measures | finalize the remaining showcase calculations and the list of typical energy saving measures and advanced measures for each typological case. | responsible: STU-K | - see below - | - |
| Task 3.5: Additional Activities | -improve the first iteration calculation model of National energy balance -explain the adopted methodology -finalize the calculations for the scenarios with most frequent/typical energy saving measures -finalize the national energy balance report | responsible: STU-K | - see below - | - |
| Deliverable D4 (Tasks 3.1 to 3.2) | Finalize the task 3.2 – checking inputs and completing the datasets-system pictures, upload the final version | responsible: STU-K | D4.12 National Building Typology Datasets | May 2011 |
| Deliverable D5 (Tasks 3.1 to 3.4) | Finalize the second draft, finish the calculations and make corrections in graphic outputs (labelling) | responsible: STU-K | D5.12 National Typology Brochure | May 2011 |
| Deliverable D6 (Tasks 3.1 to 3.5) | Elaborate a concept of report which would describe the national activities in the package WP3 and provide the linkage to used data sources and description of applied calculation methods | responsible: STU-K | D6.12 Scientific Report on National Typology Project | May 2011 (shift to Aug 2011) |
| Deliverable D7 (Tasks 3.1 to 3.3) | -the task is not relevant for the Czech Republic | responsible: IWU | D7 Report: Guideline Energy Certificate Database Use for Building Typologies | May 2011 (shift to Aug 2011) |
| Deliverable D8 (Task 3.5) | Finalize the report on the contribution of Building Typologies to National Energy Balances | responsible: IWU contributions by STU-K | D8 Report: Contribution of Building Typologies to National Energy Balances | May 2011 (shift to Aug 2011) |
| Deliverable D9 (Task 3.5) | - no contributions foreseen - | - | - | - |
| P13 – SBi – Denmark |  |  |  |  |
| Task 3.1: Acquisition of building data | Acquisition done. | responsible: SBI | - see below - | - |
| Task 3.2: Acquisition of supply system data | Acquisition done. | responsible: SBI | - see below - | - |
| Task 3.3: Acquisition of data on the frequency of building and system types | Acquisition done. | responsible: SBI | - see below - | - |
| Task 3.4: Energy balances and energy saving measures | Minor adjustment of the energy balance model by calibrating with the energy statistic. | responsible: SBI | - see below - | - |
| Task 3.5: Additional Activities | national energy balance of residential buildings: done. | responsible: SBI | - see below - | - |
| Deliverable D4 (Tasks 3.1 to 3.2) | Building data and supply data entered in the TABULA.xls | responsible: SBI | D4.13 National Building Typology Datasets | May 2011 |
| Deliverable D5 (Tasks 3.1 to 3.4) | National Typology Brochure and Display sheets are created for each example building. | responsible: SBI | D5.13 National Typology Brochure | May 2011 |
| Deliverable D6 (Tasks 3.1 to 3.5) | First draft of the national report finished. | responsible: SBI | D6.13 Scientific Report on National Typology Project | May 2011 (shift to Aug 2011) |
| Deliverable D7 (Tasks 3.1 to 3.3) | Delivered. | responsible: IWU contributions by SBI | D7 Report: Guideline Energy Certificate Database Use for Building Typologies | May 2011 (shift to Aug 2011) |
| Deliverable D8 (Task 3.5) | Delivered. | responsible: IWU contributions by SBI | D8 Report: Contribution of Building Typologies to National Energy Balances | May 2011 (shift to Aug 2011) |
| Deliverable D9 (Task 3.5) | - no contributions foreseen - | - | - | - |
| WP4: Building Typology WebTool and General Conclusions |  |  |  |  |
| Task 4.1: Development of the Building Typology Webtool | finalise the development of the webtool | responsible: IWU contributions by all partners | - see below - | - |
| Task 4.2: Start and test phase of the public Building Typology Webtool | feedbacks of the users will be collected and adaptations and corrections will be made, if necessary | responsible: IWU contributions by all partners | - see below - | - |
| Task 4.3: General Conclusions | cross-country comparison of the national building typologies examination of conditions for using the building typologies for EU-wide scenario analyses conclusions for the field of non-residential building will be drawn | responsible: IWU contributions by all partners | - see below - | - |
| Deliverable D10 (Tasks 4.1 to 4.2) | online software consisting of: online user-interface internet database calculation procedures | responsible: IWU contributions by all partners | D10 Building Typology Webtool | May 2011 |
| Deliverable D11 (Task 3.5) | report including the main results from WP 2, 3 and 4 | responsible: IWU contributions by all partners | D11 Synthesis Report SR2 | Nov 2011 |
| WP5: Communication and Dissemination |  |  |  |  |
| Task 5.1: National Dissemination | according to the national dissemination activity list of all partners, see : http://www.building-typology.eu/communication.html | co-ordination: ZRMK contributions by all partners | - see below - | - |
| Task 5.2: International Dissemination | According to the Communication Plan the third dissemination phase “National Building Typologies for 13 European Countries” was started in June 2011. The main elements are an article in the BuildUp Newsletter and the adaptation of the TABULA website showing the finalised national building typologies. In November 2011 the phase “Try the webtool” will start – experts will be invited to try the webtool and have a closer look at residential buildings in different European countries. Information about the actual project results will be given on the Buildup Web portal. Apart from this the partners will expand contacts with interested experts and key actors from non-participating countries and inform already established contacts about the project proceedings. | co-ordination: AEA contributions by all partners | - see below - | - |
| Task 5.3 Project Website | target group oriented summary of WP3 and WP4 results (systematics and application fields of the national building typologies; consequences) integration of webtool in the project website | responsible: IWU contributions by all partners | - see below - | - |
| Deliverable D12 (Task 5.1) | national conferences / workshops will be documented at the internal website: http://www.building-typology.eu/communication.html | responsible: ZRMK contributions by all partners | D12.1-13 National Conferences or Workshops | Nov 2011 |
| Deliverable D13 (Task 5.1) | publications will be documented at the internal website: http://www.building-typology.eu/communication.html | responsible: ZRMK contributions by all partners | D13.1-13 Publications in National Journals | Nov 2011 |
| Deliverable D14 (Task 5.2) | second e-mailing action | responsible: IWU contributions by all partners | D14 E-Mailing Action | Jun 2010 + Dec 2011 |
| Deliverable D15 (Task 5.2) | As regards the organisation 4 alternative locations for the international workshop were presented by AEA at the Ljubljana meeting. The EUSEW 2012 is the favourite event to attach the workshop, the exact date is still not fixed by the EUSEW. As soon as location and date are fixed possible external speakers will be contacted. Some suggestions regards to the contents of the workshop, the core theme, target groups and program were presented by IWU and discussed at the Ljubljana meeting. Apart from the external speakers the TABULA concept will be presented by IWU and examples for the work on national level (WP3) will be sketched by some of the TABULA partners. | responsible: AEA contributions by all partners | D15 European Expert Workshop “Building Typologies” | Jan 2012 |
| Deliverable D16 (Tasks 5.1 to 5.3) | finalised (see Appendix Table 1) | responsible: AEA contributions by all partners | D16 Communication Plan | Sep 2009 |
| Deliverable D17 (WP3, WP4, WP5) | The concept available (see Appendix Table 1) and tracking of the partner activities have been taking place by means of monitoring and discussing the NAG activities at project meetings. | responsible: Vito + IWU contributions by all partners | D17 Strategic Approach for Co-ordinated Activation and involvement of national Advisory Groups | concept: Sep 2009 final: May 2012 |
| WP6: IEE Dissemination Activities |  |  |  |  |
| Task 6.1: Contribution to IEE online information system | update EACI Project Fact Sheet further contributions, if possible | responsible: IWU / AEA | - | - |
| Task 6.2: Contribution to the development of additional information material | upon request | responsible: IWU / AEA | - | - |
| Task 6.3: Contribution to EU dissemination events | update EACI Project Slides further contributions, if possible | responsible: IWU / AEA | - | - |
| Task 6.4: Contribution to CA EPBD and BuildUp | Contribution to BuildUp Newsletter further contributions, if possible | responsible: IWU AEA | - | - |

## Planned meetings and dissemination activities

The next project meetings are planned as follows:

| Date | Location | Main topics |
| --- | --- | --- |
| period January to March 2012 / combined with international expert workshop | Brussels / Belgium or Vienna / Austria | finalisation of all open tasks implementation of international expert workshop dissemination + NAG implementation |

The planned dissemination activities are specified in the previous chapter (WP5 and WP6)

# Other Issues

- none -

# Appendices to the Interim Technical Implementation Report

Table 1: Updated list of submitted deliverables since starting date

| Del. N° | WP N° | Deliverable name | Month of completion | Submission with report | Project website |
| --- | --- | --- | --- | --- | --- |
| D01 | WP1 | Risk Management Plan | Sep 2009 | PR1 | http://www.building-typology.eu/downloads/intern/management/D01_RiskManagementPlan_2009-09-17.pdf (internal) |
| D03 | WP2 | Synthesis Report SR1 | June 2010 | IR1 | http://www.building-typology.eu/downloads/public/docs/report/TABULA_SR1.pdf (public) |
| D14 | WP5 | first E-Mailing-Action | June 2010 | IR1 | http://www.building-typology.eu/downloads/intern/communication/D14_FirstEMailing_28-06-2010.pdf (internal) |
| D16 | WP5 | Communication Plan | Sep 2009 | PR1 | http://www.building-typology.eu/downloads/intern/communication/D16_CommunicationPlan_2009-09-17.pdf (internal) |
| D17 | WP5 | NAG Activation Concept | Nov 2009 | PR1 | http://www.building-typology.eu/downloads/intern/communication/D17_StrategicApproachNAG_Concept_2009-11-10.pdf (internal) current state of NAG activities: http://www.building-typology.eu/communication.html |

A deliverable list with links to the current documents is maintained at the internal project website: http://www.building-typology.eu/deliverables.html

Table 2: Indicative state of advancement of hours spent (in %) since starting date per partner and per work package

*) MDH: Status from March 2010 – no input by MDH to PR2

Table 3: Updated list of main persons in charge of the action

| Participant N° | Participant short name | Family name, first name | Telephone N° | Fax N° | E-mail | Date of Change | Comment / Justification |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | IWU | Loga, Tobias | +49 / 6151 / 2904-53 | -97 | t.loga@iwu.de |  |  |
| 2 | NOA | Dascalaki, Elena | +30 / 210 / 810-9143 | -3236 | edask@meteo.noa.gr |  |  |
| 3 | ZRMK | Sijanec Zavrl, Marjana | + 386 128 083 42 | + 386 128 0831 91 | marjana.sijanec@gi-zrmk.si |  |  |
| 4 | POLITO | Vincenzo Corrado | +39/011/090-4456 | +39/011/090-4499 | vincenzo.corrado@polito.it |  |  |
| 5 | ADEME | Despretz, Hubert | +33 4 93 95 79 44 | +33 4 93 65 31 96 | hubert.despretz@ademe.fr |  |  |
| 6 | Energy Action | Roarty, Charles | +353 1 454 5464 | +353 1 454 9797 | manager@energyaction.ie |  |  |
| 7 | VITO | Van Holm, Marlies | +32/ 14/ 33 59 97 | +32/ 14/ 32 11 85 | marlies.vanholm@vito.be | December 2010 |  |
| 8 | NAPE | Popiołek, Malgorzata | +48 22 50 54 738 | +48 22 825 86 70 | mpopiolek@nape.pl |  |  |
| 9 | AEA | Amtmann, Maria | +43 / 1 / 5861524-193 | -340 | maria.amtmann@energyagency.at | August 2010 |  |
| 10 | SOFENA | Georgiev, Zdravko | +359 2 9434909 | +359 2 9434401 | zgeorgiev@sofena.com |  |  |
| 11 | MDH | Karin Spets | +46 21 10 13 81 | +46-21-101480 | karin.spets@mdh.se | March 2011 |  |
| 12 | STU-K | Vimmr, Tomas | +420/244466217 | 244461536 | t.vimmr@stu-k.cz |  |  |
| 13 | SBi | Wittchen, Kim B. | +45 99 40 23 79 | +45 45867535 | kbw@sbi.dk |  |  |

Further Appendices

- Summary Slides (no change since last update, will be revised after publication of WebTool and Typology Brochures in November 2011)

- Project Fact Sheet (no change since last update, will be revised after publication of WebTool and Typology Brochures in November 2011)